## Slide 1: System Partner Reporting – Analysis Summary Report Partner updates at 42-months
Sportengland.org

## Slide 2: Executive summary (1)
Working as a consortium, Ipsos, NPC (New Philanthropy Capital) and Sheffield Hallam University (SHU) were commissioned by Sport England to undertake the Collective Evaluation and Learning for System Partners.
This report presents a thematic analysis of the 42-month reporting submitted by 137 System Partners, covering the period of May to October 2025. Partners self-reported progress against the Collective Evaluation and Learning Theory of Change (TOC), alongside summary statements, goal updates and learning.
The analysis underpinning this report draws on pre-existing analytical frameworks used in previous reporting. As with the last 36-month report, this round an AI model was utilised to code, rate and analyse evidence, with human quality assurance.
Progress against the System Partner TOC (headlines from the latest 6-month period, slides 7-24):
Developing as a System Partner: There is strong and wide-ranging progress embedding learning cultures, system‑thinking capability, governance and people plans; there is also growing but uneven use of digital/data to inform strategic decisions.
Organisational strategies and policies: Partners' strategies and plans are more clearly aligned to Uniting the Movement (UTM) and tackling inequalities; safeguarding, EDI and environmental policies have been strengthened, though evidence of embedding these day‑to‑day is variable.
Collaborative working: Partnerships are more deliberate, structured and place‑based, spanning health, education, local government, VCSE and sport; there is evidence of increased access to decision‑making settings, but measurement of impact of collaborations remains limited.
Engaging with communities: Partners report deeper, relationship‑based engagement using lived experience, youth/community voice, peer research and co‑design; targeting of communities facing the greatest inequalities is growing, but capacity to monitor this engagement is still mixed.
Delivering change for communities: Conditions for activity are improving through more tailored, safe and inclusive offers; there are stronger workforce, better physical and social environments for activity, and clearer referral pathways; evidence of outcome measures are positive but not standardised across the system.
Contributing to UTM: There is broad alignment with UTM outcomes, with targeted work in underserved groups and signs of system‑level shifts (governance, welfare, insight‑led targeting, locally led approaches); though the caveat is that evidence is largely self‑reported and not comparable at population level.

## Slide 3: Executive summary (2)
What partners are learning (slides 25-30)
The operating model is shifting from programme delivery towards convening, facilitation and system leadership, enabled by clearer structures, governance and proportionate MEL.
Collaboration works best when power, equity and lived experience are addressed explicitly; co-production and community/youth leadership strengthen legitimacy and sustainability.
Monitoring, evaluation and learning are moving from counting outputs to evidencing meaningful change; mixed‑methods and early, proportionate evaluation with community partners are key.
Key challenges (slides 31-37)
Capacity and capability constraints across staff, volunteers and specialist skills (safeguarding, MEL, EDI, digital), alongside financial pressures.
Governance transitions (leadership changes, restructures, compliance workloads) that are necessary but resource‑intensive.
System complexity and instability (devolution, NHS/ICB change, education pressures) requiring repeated relationship‑building and making long‑term planning difficult.
Operational demands of digital transformation and evidencing system‑level change; sustaining inclusive, place‑based work at depth with finite resources.
Progress against KPIs (slides 38-50)
131 of 137 partners (96%) provided evidence against the Theory of Change. Nearly three-quarters (72%) showed significant progress, and one-quarter (26%) Some.
By TOC area: strongest evidence of Significant progress in meeting community needs and developing as system partners; comparatively lower for amending processes and structures. Learning is most advanced in collaborative practices and meeting community needs.
Themes from summary statements (slides 51-57)
Partners are working towards UTM outcomes, strengthening governance and MEL, and beginning climate/ active‑environment work.
Overall trajectory
The portfolio is maturing from activity‑led delivery to more systemic, insight‑led and equity‑focused practice, with clearer roles as convenors and brokers in local systems; evidencing later‑stage, system‑ and population‑level change remains a shared development priority.

## Slide 4: System Partner Theory of Change

## Slide 5: Summary findings from the TOC reporting (1)
The Theory of Change (TOC), developed during evaluation scoping, sets out the shared understanding of how the System Partner investment portfolio is expected to achieve Sport England’s desired outcomes for the SPA sector. During the 42-month reporting period, Sport England continued the approach introduced at 36-months that embedded the System Partner Collective Evaluation and Learning TOC into reporting. Evidence from System Partner submissions over this period has been analysed against the TOC, and this report presents high‑level progress and illustrative examples for each of its key outcomes. The analysis indicated the following:
Developing as a System Partner:
There is strong and wide‑ranging progress in developing the culture and capability required for a System Partner role. Many organisations report embedding learning cultures, more systematic monitoring, evaluation and learning approaches, and growing, though uneven, adoption of systems thinking.
Workforce and governance changes are prominent, including new or reconfigured leadership and insight roles, revised structures, and strengthened boards and sub‑committees to support system leadership. Digital and data tools are increasingly used, but the extent to which they systematically inform strategic decisions varies.
Organisational strategies and policies:
Most partners have refreshed or developed strategies, business plans and people plans that are more clearly aligned to UTM and focused on tackling inequalities, with a discernible shift from direct delivery towards system convening and place‑based working.
Governance and core policies (e.g. safeguarding, EDI, managing complaints, environmental sustainability, HR and wellbeing) have been strengthened across the portfolio. However, evidence on consistent implementation and day‑to‑day embedding of these policies remains limited and uneven.
Collaborative working:
Collaborative working is increasingly described as a deliberate way of operating, supported by stakeholder mapping, partnership frameworks and place‑based models. There is extensive evidence of deeper, trust‑based relationships across health, education, local government, VCSE and sport bodies.
Emerging practice around power‑sharing and community or youth leadership is visible, though not yet widespread. System Partners are gaining greater access to decision‑making arenas (e.g. ICSs, Health and Wellbeing Boards, Combined Authorities).

## Slide 6: Summary findings from the TOC reporting (2)
Engaging with communities:
Many organisations have progressed from one‑off consultation to more sustained, relationship‑based engagement, with wider use of community insight, lived experience, peer research and structured youth and community voice to shape provision.
There is emerging but variable evidence that engagement is increasingly targeted at communities facing the greatest inequalities, and that co‑design and locally led models are helping to tailor offers. However, monitoring and evaluation capacity and consistent outcome data remain constraints.
Delivering change for communities:
Evidence indicates that conditions for people and communities to be active are improving, through more accessible and tailored opportunities, safer and more inclusive cultures, and adapted physical and social environments (e.g. community hubs, parks, school and faith‑based settings).
System Partners are moving from discrete projects towards more embedded system change, including integration of physical activity into health, social care, education and planning processes, and greater emphasis on workforce, leadership and digital infrastructure. Across a range of partner‑level monitoring and evaluation data, there are reported positive shifts in participation, experiences and, in some cases, inactivity among those reached.
Contributing to Uniting the Movement:
Collectively, the data indicate that System Partners are closely aligned with the strategic aims of UTM, with widespread targeting of groups experiencing the greatest inequalities and contributions across all four UTM outcomes (increased activity, reduced inactivity, reduced inequalities, and improved experiences and safeguarding for children and young people).
There is emerging evidence of system‑level shifts, including strengthened governance and welfare standards, routine use of insight to target resources, and locally led, co‑designed approaches that are helping to make activities better suited to local needs and, in some cases, to sustain provision over time. However, the evidence is largely self‑reported and based on diverse indicators, timeframes and geographies. As a result, the findings provide indicative examples of contribution rather than a comprehensive or comparable assessment of population‑level or long‑term impact.

## Slide 7: Overall pattern of change in System Partners’ progress
The progress of the System Partner portfolio was assessed from the 12-month reporting period up until the 42-month report. The findings show:
Themes | Evidence
From activity delivery to more systemic ways of working | Earlier evidence focused on programmes and early partnership activity; over time, reporting shows a stronger emphasis on changing organisational culture, ways of working and relationships as a route to impact. Many partners now describe deliberate roles as convenors, connectors and facilitators within local systems, rather than primarily as direct deliverers.
Strengthening organisational capability and infrastructure | There is sustained progress in governance, safeguarding, EDI, people plans and workforce development, alongside increased use of insight, digital tools and structured MEL. Learning cultures and systems‑thinking language are increasingly evident, with more examples of reflective practice and decision‑making informed by evidence.
Maturing collaboration and place-based working | Collaboration has shifted from ad‑hoc or bilateral arrangements towards more structured, multi‑stakeholder partnerships, often anchored in specific places. Partners more frequently describe shared governance, joint planning and a stronger role in decision-making across across health, education, local government and VCSE sectors.
Deepening community engagement and ownership | Engagement has generally moved from one‑off consultation to more sustained relationships, including community insight, lived experience approaches, youth and community voice structures, and co‑design. There is growing evidence of communities and local organisations leading or sustaining activity, particularly in areas and groups experiencing the greatest inequalities.
Increasing focus on outcomes and inequalities | Over time, partners provide richer evidence on participation, inactivity, experiences and equity, with clearer targeting of under‑represented groups and stronger narrative links between their work and changes in conditions for people to be active. While measures are not standardised, more partners now report outcome data (including some social value and wellbeing measures) rather than only describing activity delivered.

## Slide 8: Where progress has been consistent, or uneven
Consistent progress
Consistent strategic intent but variable depth of change:
Partners maintain a strong stated commitment to tackling inequalities and improving experiences, and continue to align their work with the overarching strategic outcomes.
However, the depth and maturity of change vary between organisations: some provide detailed evidence of embedded practice and systems influence, while others remain more focused on describing structures, policies or isolated initiatives.
Stronger evidence for organisational change than system change:
The most consistent and well‑evidenced progress is within organisations themselves (culture, structures, workforce, governance and MEL).
Evidence on sustained changes in local systems, long‑term community outcomes and population‑level impacts remains more fragmented and often short‑term or self‑reported.
Uneven progress
Uneven progress on equity, power‑sharing and lived experience:
References to working with communities facing the greatest inequalities increase over time, and there are more examples of co‑design, ambassadors and peer roles.
Nonetheless, practice around sharing power and leadership with communities is not yet widespread, and evidence on how these approaches affect participation patterns and experiences for different groups remains patchy and uneven across places.
Persistent data and measurement limitations:
Across the period, partners use diverse indicators, baselines and timeframes, limiting comparability and making it difficult to aggregate or attribute change beyond illustrative examples.
Monitoring and evaluation capacity is still uneven across the portfolio.
Overall trajectory of progress:
Taking the evidence together, System Partners have moved along a broadly consistent trajectory from describing activities and early collaborations towards demonstrating more systemic, insight‑led and equity‑focused practice.
At the same time, core challenges around evidencing later‑stage change (in systems, communities and inequalities) remain and need to be borne in mind when interpreting progress since the earliest reporting.

## Slide 9: Learning

## Slide 10: Summary of learning
This section presents themes from the learning updates that System Partners submitted against the Theory of Change. AI was used to assess System Partner updates against the Theory of Change, rating their alignment with identified themes. Updates were further analysed by AI to summarise key activities and learning, presented here as "What works“ and "What doesn't work". These themes include:
The data indicates a clear shift from delivery to systemic work. Organisations are increasingly acting as convenors and brokers, investing in local connectors, leadership and workforce so that communities and partners can design, lead and sustain activity themselves.
There is emerging evidence that stronger internal structures, governance and learning systems are enabling this shift. Co‑designed theories of change, proportionate MEL frameworks, refreshed policies (e.g. safeguarding, EDI, environmental sustainability) and clearer roles are improving accountability, resilience and the use of evidence in decision‑making.
Across the system, partners are prioritising deep listening, trust‑building and co‑production with communities. Tailored, culturally relevant offers and “you said, we did” feedback loops are helping to address inequalities and ensure provision reflects local needs, rather than standardised, sport‑first models.
The data shows that collaboration is most effective where power, equity and lived experience are addressed explicitly. Embedding community and lived‑experience voices in governance and design is strengthening legitimacy and generating more trusted, sustainable solutions.
Monitoring, evaluation and learning practice is shifting from counting outputs to explaining complex change. Mixed‑methods approaches that combine quantitative data with stories and lived experience are helping partners understand who is benefiting, how behaviour and culture are changing, and where gaps remain.
Organisations report that system change is constrained by capacity, the complexity of working across multiple shifting systems (e.g. health, local government, VCSE), and risks to continuity when work depends on a small number of individuals.. Progress stalls where change outpaces communication, reporting demands are disproportionate, or there is insufficient succession planning and business continuity in place.
Looking ahead, partners intend to focus on fewer, deeper collaborations in places and communities facing the greatest inequalities, embed learning and evaluation from the outset, and use shared evidence more deliberately to influence commissioning, policy and organisational culture in line with Uniting the Movement.

## Slide 11: Challenges

## Slide 12: Summary of challenges
This section presents some of the themes related to challenges that System Partners are facing, as reported in their Summary Statements, Goal blockages information and Theory of Change updates.
These challenges are grouped into four key themes:
Capacity & capability: System Partners increasingly report operating at or near full stretch, with small teams, recruitment and retention challenges, and inflationary pressures constraining both delivery and strategic work. Specialist skills in areas such as safeguarding, MEL, digital and EDI are in demand but often under‑resourced, limiting the extent to which organisations can fully embed more insight‑led, co‑produced and digitally enabled approaches.
Governance challenges: Many organisations are managing significant governance change – including CEO and leadership transitions, board refreshes and restructures – to align with new strategies and geographies, but these processes temporarily reduce capacity and require intensive communication. At the same time, meeting governance codes, safeguarding standards and EDI commitments is resource‑intensive, particularly for smaller NGBs and charities, and cultural change in decision‑making is recognised as long‑term work.
Working in complex systems: Partners are operating within rapidly shifting local government, devolution and NHS/ICB structures, which create uncertainty, require repeated relationship‑building and can slow long‑term planning. Health and education systems face acute operational and financial pressures, making it harder to prioritise prevention, physical activity and co‑designed work, even as place‑based collaborations mature at different speeds across geographies.
Other operational and programme challenges: Organisations are working to design and sustain inclusive programmes for those facing the greatest inequalities, but such provision is more resource‑intensive and often difficult to fund sustainably, with participation and membership growth under pressure in a challenging economic context. Digital transformation and strengthened monitoring and evaluation are progressing, yet both are described as slower and more demanding than anticipated, especially where outcomes relate to culture, relationships and system conditions rather than simple participation counts.

## Slide 13: Evolving challenges
Since the start of the investment, System Partners have reported a set of consistent core challenges, but that are also growing in complexity.
System Partners continue to operate with constrained capacity and capability. Small, often overstretched teams face ongoing recruitment and retention difficulties at all levels, including specialist roles (e.g. safeguarding, MEL, digital, EDI, insight) and the talent/coaching workforce, alongside declining or fragile volunteer capacity. These pressures are closely linked to financial constraints: rising costs, inflation and squeezed public budgets limit the ability to sustain posts, invest in skills and maintain inclusive offers.
Governance has shifted from isolated leadership changes to wider programmes of organisational reform. Many partners are managing CEO transitions, restructures and board refreshes at the same time as meeting demanding governance, safeguarding and regulatory requirements. Efforts to integrate lived experience and EDI more fully into decision‑making are positive but require new structures, cultural change and time, adding to short‑term strain on leadership and governance capacity.
Contextual challenges increasingly reflect the complexity and instability of the systems in which partners operate. Frequent changes in local government structures, devolution arrangements and NHS/ICB configurations, combined with acute pressures in health and education, make long‑term planning difficult and require repeated relationship‑building. While collaboration is widely valued, partners report variable “system readiness”, uneven engagement and the time‑ and resource‑intensive nature of place‑based work, raising questions about how to sustain depth of work across multiple places.
Operationally, partners highlight persistent challenges around participant engagement and retention, particularly for underserved groups, and around equity and affordability within talent pathways. Inclusive provision is more resource‑intensive and harder to fund sustainably, and the cost burden on families can limit progression.
Finally, digital transformation and the drive to become more evidence‑led have themselves become major areas of challenge. Implementing new CRMs, competition and membership systems, and strengthening MEL and insight, are seen as essential but are slower, more disruptive and more demanding than anticipated. Many partners still struggle to capture proportionate data from community organisations and to evidence cultural and system‑level change, even as expectations around insight‑led decision‑making increase.

## Slide 14: Progress against KPIs – overview and commentary

## Slide 15: System Partners: key Performance Indicators
Of the 137 System Partners currently funded through this investment, 131 (96%) provided some data against the TOC outcomes. This is an improvement on the previous round of reporting (e.g. with 93% of System Partners reporting at 36-months).
6 System Partners did not provide data against the TOC so were not included in the analysis. This is due to either late or no submissions of reporting.
A few System Partners only completed one or two of the outcomes with progress and learning updates. Ratings were adjusted to account for this.
The proportion of System Partners who have evidenced significant progress against the six TOC outcomes remains high (see next slide), though lower than reporting rounds before 36-months due to the change in methodology to create more nuanced scores.
There are some differences in quality of information across the System Partners and the TOC outcomes which has created more mixed quality of information scores, though a large proportion are still rated as good.
Generally, there is less significant evidence of learning compared to progress. This could be how System Partners are articulating their learning, for example they may state a learning statement but not explain how this was learned or what they have done as a result of the learning.
By evidencing progress or learning, we mean the information and data provided by System Partners in reporting suggests that there is Significant/Some/Limited progress and learning against the different Theory of Change outcomes.
Proportion of System Partners providing data against the Theory of Change outcomes
Chart: 
| Provided evidence | Did not provide evidence
% | 96 | 4
Base: All System Partners – 137

## Slide 16: KPI Dashboard
Chart: Evidence of progress across SPs
| 36-months | 42-months
Significant | 0.49 | 0.72
Some | 0.46 | 0.26
Limited | 0.06 | 0.02
Chart: Evidence of learning across SPs
| 36-months | 42-months
Significant | 0.23 | 0.72
Some | 0.43 | 0.18
Limited | 0.35 | 0.1
Chart: Quality of information across SPs
| 36-months | 42-months
Good | 0.33 | 0.63
Mixed | 0.47 | 0.34
Needs improvement | 0.2 | 0.04
The adapted KPI analysis developed at 42-months was re-run on 36-month data to allow for comparison, with consistent approaches to the ratings.
It shows there have been significant improvements in the evidence of progress, learning and quality of information in the last 6 months.
The following slide also shows how progress and learning updates have improved across all areas of the TOC.
Base: System Partners – 131 (42 months) and 127 (36 months)
Significant
Some
Limited
Good
Mixed
Needs improvement

## Slide 17: Variation in progress across TOC
Across all areas of the TOC, there have been increases in the proportion of System Partners rated as showing ‘Significant’ progress,
The largest improvements in the proportion ‘Significant’ progress among the TOC outcomes are for ‘Conditions change’ (up from 57% to 73%) and ‘Collaborative practices’ (up from 77% to 95%).
Between 36-months and 42-months, for ‘Conditions change’ across partners there is evidence of a clearer shift from “testing and piloting” towards consolidating and scaling approaches that change local conditions (e.g. more systematic use of insight, stronger governance, and sustained place‑based models in schools, health and community settings).
For ‘Collaborative practices’, compared with 36 months, many System Partners now describe more structured, multi‑year collaborations (e.g. formalised MOUs, strategic advisory groups, new governance/steering structures), indicating a shift from ad‑hoc partnership working to clearer shared purpose and accountability.
Chart: 
| Uniting the Movement - 36 months | Uniting the Movement - 42 months | Conditions change - 36 months | Conditions change - 42 months | Meet community needs - 36 months | Meet commuity needs - 42 months | Collaborative practices - 36 months | Collaborative practices - 42 months | Amend processes and structures - 36 months | Amend processes and structures - 42 months | Understand and support changes - 36 months | Understand and support changes - 42 months
Significant | 0.63 | 0.73 | 0.57 | 0.73 | 0.69 | 0.84 | 0.77 | 0.95 | 0.58 | 0.67 | 0.76 | 0.87
Some | 0.23 | 0.19 | 0.29 | 0.18 | 0.21 | 0.15 | 0.18 | 0.05 | 0.33 | 0.25 | 0.2 | 0.12
Limited | 0.14 | 0.07 | 0.14 | 0.09 | 0.1 | 0.02 | 0.05 | 0.01 | 0.09 | 0.07 | 0.03 | 0.01
Understand and support changes
Amend processes and structures
Collaborative practices
Meet community needs
Conditions change
Uniting the Movement
42 months
36 months
42 months
36 months
42 months
36 months
42 months
36 months
42 months
36 months
42 months
36 months
Base: System Partners – 131 (42 months) and 127 (36 months)

## Slide 18: Variation in learning across TOC
Across all areas of the TOC, there have been improvements in evidence of learning from System Partners.
There are substantial improvements in ‘Significant’ learning for ‘Understand and support changes’ (up from 52% to 76%) and ‘Uniting the Movement’ (up from 21% to 49%). Similarly to progress, ‘Collaborative practices’ also saw a large increase from 46% up to 71%.
Between 36-months and 42-months, for ‘Understand and support changes’ across System Partners, the more recent six‑month updates place greater emphasis on how learning and systems‑thinking are being operationalised (e.g. new operating models, use of theories of change, refined MEL tools), whereas 36-month reports focused more on describing activities and intentions.
For ‘Uniting the Movement’, at 42-months, there is a clearer focus on system‑level change, with many partners describing how they are influencing strategies, commissioning, planning processes and governance (e.g. health boards, transport plans, talent pathways, safeguarding frameworks), rather than only reporting programme delivery and participation numbers.
Chart: 
| Uniting the Movement - 36 months | Uniting the Movement - 42 months | Conditions change - 36 months | Conditions change - 42 months | Meet community needs - 36 months | Meet commuity needs - 42 months | Collaborative practices - 36 months | Collaborative practices - 42 months | Amend processes and structures - 36 months | Amend processes and structures - 42 months | Understand and support changes - 36 months | Understand and support changes - 42 months
Significant | 0.21 | 0.49 | 0.34 | 0.55 | 0.54 | 0.75 | 0.46 | 0.71 | 0.4 | 0.54 | 0.52 | 0.76
Some | 0.35 | 0.24 | 0.32 | 0.31 | 0.23 | 0.19 | 0.33 | 0.2 | 0.27 | 0.29 | 0.34 | 0.17
Limited | 0.44 | 0.28 | 0.34 | 0.14 | 0.24 | 0.06 | 0.21 | 0.09 | 0.33 | 0.17 | 0.14 | 0.07
Understand and support changes
Amend processes and structures
Collaborative practices
Meet community needs
Conditions change
Uniting the Movement
42 months
36 months
42 months
36 months
42 months
36 months
42 months
36 months
42 months
36 months
42 months
36 months
Base: System Partners – 131 (42 months) and 127 (36 months)

## Slide 19: Themes from Summary Statements

## Slide 20: Summary Statement themes
Systems change and place‑based working:
Partners report steady to strong progress, with many shifting from direct delivery towards convening, influencing and enabling more equitable local systems, often through place‑based approaches
Tackling inequalities and engaging minoritised groups:
There is extensive activity focused on disabled people, people with long‑term health conditions, women and girls, ethnically diverse communities and those in low‑income areas, increasingly using intersectional and culturally competent approaches.
Positive experiences for children and young people:
Work with children and young people is widespread and maturing, with School Games, school‑to‑community links, trauma‑informed and mental‑health‑aware practice, and talent pathways increasingly geared towards positive experiences rather than participation volume alone.
Increasing physical activity and reducing inactivity:
Many organisations describe stabilising or growing participation in specific formats and audiences, alongside a stronger emphasis on improving the conditions for activity (safe, welcoming, inclusive environments) rather than only expanding session numbers.
Governance, organisational development and culture change:
Governance, culture and workforce capabilities are strengthening through board reviews, DIAPs, safeguarding frameworks, learning cultures and new workforce pathways, although capacity constraints, staff turnover and change fatigue remain common challenges.
Evaluation methodology and learning:
Evaluation and learning are becoming more embedded, with wider use of structured insight tools, CRMs and communities of practice, but data gaps (particularly on disability, ethnicity and local variation), inconsistent reporting and limited MEL capacity constrain system‑wide understanding.
.
Climate, environment and active environments / active travel:
Climate action, environmental sustainability and active environments/active travel are emerging areas of focus, though activity is uneven across partners and often at an early or pilot stage relative to other themes.
Cross‑cutting challenges:
Partners highlight financial and commissioning uncertainty (including devolution, health system change and school sport reforms), facility access and costs, volunteer and workforce capacity, and the time and complexity involved in shifting organisational and system culture.

## Slide 21: Developing organisations
What has changed in the last 6 months for System Partners?
System Partners are moving from designing and piloting new strategies, structures and programmes (e.g. new LMS, membership systems, talent models, School Games redesigns, DIAPs, club hubs) towards embedding these changes in routine practice, with clearer theories of change, place‑based plans and refined operating models.
Activities have shifted from largely exploratory or one‑off initiatives to more targeted, insight‑led delivery and place‑based work, often focused on specific audiences (e.g. KS2 girls, disabled people, CYP in AP, faith‑based communities) and underpinned by stronger local governance and partnership structures.
Organisations report greater systems‑thinking capability, stronger governance and compliance (Code of Sports Governance, CPSU, Ann Craft Trust, DIAPs), and more confident roles as convenors, critical friends and system influencers across health, education, local government and devolution agendas.
There is a clearer emphasis on learning, evaluation and evidence use (e.g. use of maturity matrices, Power BI, Ripple Effect Mapping, social value studies), with partners increasingly using insight to adapt programmes, refine workforce development and inform policy engagement.
What remains consistent?
Across both reporting periods, partners consistently emphasise a shift from direct delivery towards systems thinking and place‑based working—using their convening role, local insight and multi‑agency partnerships to influence wider strategies, governance and investment rather than acting solely as programme deliverers.
In both periods, there is a strong, sustained focus on tackling inequalities and improving experiences for children and young people, with partners targeting under‑served groups, strengthening youth voice and leadership, and using schools and community settings as key entry points into physical activity.

## Slide 22: Goal analysis

## Slide 23: Progress against goals
Across the 2,976 agreed goals, partners report strong progress
System Partners were asked to self-rate their progress against their goals (Completed/Achieved, Excellent, Good, Some, No change) and asked to provide additional information if they said they need support, are struggling, the goal is blocked, no longer relevant or needs changing.
In October 2025, partners have reported that a large proportion of goals and steps are showing positive progress. Figure 1 shows nearly two thirds (65%) of the goals that System Partners are progressing (i.e. Not blocked in anyway) are ‘Good’ (47%) or ‘Excellent’ (18%). Some roles (Governing and Talent) focus more on achieving standards or success measures, which is reflected in a slightly higher number of completed goals and steps (see Figure 2). Systemic goals have the largest proportion showing ‘Good’ (51%) and ‘Excellent’ (20%) progress, which could reflect how most System Partners will have goals linked to this role.
Around one in twenty (5%) of all goals are blocked in some way, most of these (6%) need changing, some need support (2%) and less than 1% are blocked, need support or are no longer relevant.
*Base sample excludes goals marked as blocked/struggling/needs support/needs changing/no longer relevant
Chart: Figure 1: Overall Partner Goal & Step progress (sample of 2,976*)
| Completed | Excellent | Good | Some | No change
Column1 | 0.038306 | 0.18347 | 0.47245 | 0.22211 | 0.083669
Chart: Figure 2: Goal & Step progress by role
| Delivery | Governing | Systemic | Talent
Completed | 0.03 | 0.07 | 0.02 | 0.05
Excellent | 0.17 | 0.16 | 0.2 | 0.18
Good | 0.46 | 0.46 | 0.51 | 0.38
Some | 0.24 | 0.23 | 0.2 | 0.28
No change | 0.1 | 0.08 | 0.07 | 0.1
Column1

## Slide 24: Thank you

## Slide 25: Where to go for more information
The latest Learning Synthesis report (June 2025) for the Collective Evaluation and Learning is available here: System partners evaluation - learning synthesis June 2025.pdf
The 36-month System Partner report is available here: System Partner 36 month report.pptx
There is more information for System Partners, including on the reporting process, here: System Partner Hub – Home
The slides from the peer learning session on 36-month report insights are here: SP reporting - insights from 36 month reports Aug 2025.pdf
The recording from the peer learning session on 36-month report insights is here: SP reporting insights peer learning session write up_Aug 2025.pdf

## Slide 26: Appendix

## Slide 27: Overview of methods (1)
As part of the System Partner portfolio of work, Sport England asks System Partners to submit 6-monthly self-reported updates of progress towards their self-defined goals, alongside other information. These updates are submitted online via SmartSheet and are then analysed at the aggregate level.
The 42-month reporting followed the same structure as 36-month, which saw more significant changes to how System Partners provide updates to Sport England. This included:
Reporting on progress and learning against the outcomes of the TOC
  Developing as a System Partner
  Organisational strategies and policies
  Collaborative working
  Engaging with communities
  Delivering change for communities
  Contributing towards UTM
Self-rating on progress against goals and reporting on challenges or blockages experienced by System Partners that may affect progress against their goals.
Summary statements on the role of being a System Partner and an overview of progress made in the past six months for each of the funded roles – systemic, governing, delivery and talent.
Previous analysis of System Partner reporting used an analytical approach and framework for reviewing System Partner updates at 6-months by Ecorys and Sport England in 2023. This approach was replicated by the Collective Evaluation and Learning partner for the 12-month report. A revised approach was agreed with Sport England for the 24-month report, which sought to streamline the approach and report against the Collective Evaluation and Learning Theory of Change. It was also used for the 30-month report.
For the 42-month (and the previous 36-month report), the Collective Evaluation and Learning partner adapted the existing analytical approach and framework to be used by an Artificial Intelligence (AI) Model known as a Large Language Model (LLM). They are a specific type of AI that have been trained on vast amounts of text data enabling them to understand and analyse large amount of text. The AI model was used to: summarise the data submitted by System Partners, identify themes (e.g. of progress / barriers to progress) and rate level of progress, learning and quality of evidence.

## Slide 28: Overview of methods (2)
Examples of how the AI model was used in the analysis include:
AI was used to identify themes within the progress and learning columns of each TOC outcome. These themes could be compared against those from the previous reporting round to see what has changed or what has remained consistent.
AI analysed the Summary Statement data provided based on themes related to the four UTM outcomes and sense checked the learning themes identified in the latest evaluation learning synthesis report. The themes were adapted accordingly and examples of activities and evidence provided related to these themes across the portfolio is presented in the report.
AI was also used to assess, as a System Partner level, progress and learning against the Theory of Change providing a rating of their progress and learning. Quality of evidence was also rated and the AI generated feedback on how System Partners could improve their submissions. The approach to these ratings was amended from 36-months to produce more meaningful variations in scores and to ensure AI recognised the value of different types of evidence (e.g. not just quantitative data) and styles of updates (e.g. lots of information about one activity, or less detail about multiple activities).
AI was used to analyse progression and changes in themes around challenges, learning and the Theory of Change across the entire period of the System Partner investment. AI reviewed evidence included in reports from the 12-month System Partner reporting period onwards, and compared this against the most recent findings. The findings of these changes, as well as what has remained consistent, are presented in the relevant sections of this report (TOC slides 11-12, Challenges slide 33 and Summary statements slide 57).
As with at 36-months, the ratings of progress, learning and quality of information against the TOC have been used to inform the KPIs.
More detail on the use of AI and its limitations are set out in slide 39-40.

## Slide 29: Approach for use of AI in SP reporting analysis (1)
Our approach to analysis of System Partner updates against the Theory of Change to produce the progress, learning and quality of information ratings was based on an existing approach and coding framework developed by Ecorys with input from Sport England for the System Partner Thematic Review at 6-months.
How did we use AI to produce ratings?
The progress and learning updates against each TOC outcome was analysed by AI to assign 1-100 scores for Progress, Learning and Quality of Information/Evidence. These scores were then mapped to the existing ratings framework: ‘Significant’, ‘Some’ or ‘Limited’ evidence of progress/learning. Each of these updates was also assessed with a ‘Quality of information’ score of ‘Good’, ‘Mixed’ or ‘Needs improvement’.
The thresholds for these ratings are included in the table below and depended on how many TOC outcomes the SP updated against (i.e. if they reported on all 6 outcomes then their rating was based on the range in the top row – they needed at least 510 to get a score of ‘Significant’, between 504 and 390 for ‘Some’ and 384 or less for ‘Limited’).
“Not applicable” or non-updates were scored 0; very low scores were sense-checked and adjusted to 0 where responses were clearly not progress/learning updates.
An overall score was aggregated for each System Partner to reflect their overall progress, learning and quality of information across all the TOC outcomes. This is presented in the progress against KPIs section.
There are also breakdowns of progress and learning by SP role (Systemic, Delivery, Talent and Governing). This was assessed by the overall score that the SP with these roles was rated. The individual progress and learning rating for each TOC outcome is also presented in this report.
No. of outcomes reported on | Significant | Some |  | Limited
6 | 510 | 504 | 390 | 384
5 | 425 | 420 | 325 | 320
4 | 340 | 336 | 260 | 256
3 | 255 | 252 | 195 | 192
2 | 170 | 168 | 130 | 128
1 | 85 | 84 | 65 | 64
No. of outcomes reported on | Good | Mixed |  | Needs improvement
6 | 480 | 474 | 360 | 354
5 | 400 | 395 | 300 | 295
4 | 320 | 316 | 240 | 236
3 | 240 | 237 | 180 | 177
2 | 160 | 158 | 120 | 118
1 | 80 | 79 | 60 | 59

## Slide 30: Approach for use of AI in SP reporting analysis (2)
AI was provided with the review framework definitions of the Progress, Learning and Quality of Information ratings, and then given additional descriptions via prompts of ‘what good looks like’ and how this maps to a 1-100 score. The review frameworks and prompts used are included in the following three slides.
This was an iterative approach with test-runs on data and spot checking by humans with a quarter of AI scores and explanations reviewed. As a result of this review, amends were made to prompts to improve the range of scores provided and the suggestions for improvement that AI was providing. For example, it was evident that AI was favouring quantitative data as ‘Significant’ or ‘Good’ over other types of evidence, so we fed in a prompt that gave AI guidance on how to look for other types of evidence.
We also provided AI with some additional contextual information on the System Partner investment more broadly and what ‘Uniting the Movement’ is in language AI could best understand. Here is an example:
  Uniting the Movement (UTM) is a strategic initiative to revamp the Sports and Physical Activity (SPA) sector by fostering trust-based partnerships with System Partners (SPs) to enhance participation and address inequalities among all age groups.
The ratings and explanations of the ratings from AI were reviewed and spot checked by the evaluation team, looking particularly for outliers and distribution of scoring – prompts were refined where inconsistencies were spotted and these new prompts were used to re-run 36-month data for like-for-like comparison. Trend comparisons before 36-months on the KPI ratings should be treated with caution due to the change in methodology.
How else did we use AI in this report?
AI was also used to synthesise key themes from progress/learning updates (especially those rated Significant), identify illustrative examples included throughout the report, and analyse themes across learning, challenges and summary statements.
Individual partner reports present Significant/Some/Limited and Good/Mixed/Needs improvement ratings (not the numeric scores) and include AI-generated explanations and suggestions for improvement. These documents were subject to additional QA and should be reviewed with the supporting document.
Evidence submitted is self-reported with varying indicators and styles of presenting evidence. AI can be sensitive to language style – which is partly mitigated through explicit prompt guidance on evidence types and proportionate human QA. However, as a result findings presented should be viewed in context of other evidence and evaluation outputs.

## Slide 31: The review frameworks – progress
Rating level | Description of rating
Significant | ‘Significant’ progress is when the TOC outcome can be considered achieved or is close to being achieved. Progress could also be considered ‘significant’ if sizeable barriers to achieving the TOC outcome have been removed, meaning completion will follow with relative ease.
Some | ‘Some’ progress is when steps towards achieving the TOC outcome have been made, though the goal is not yet achieved or close to being achieved.
Limited | ‘Limited’ progress is when there has been no, or little, progress made towards the the TOC outcome. This may relate to challenges such as capacity issues, or a need to prioritise alternative goals.
None/ N/A | This cell is left blank.
Prompts provided to AI to calculate Progress ratings:
Evidence and/or explanations about progress towards the outcome, with a score ranging from 100 when significant, to 1 when limited. The score depends on the steps and how they contributed to the progress towards the outcome. It could be multiple meaningful steps with good evidence and/or explanations, one or a few significant steps with extensive evidence and/or explanations, or a combination of both.
Progress should be described in context and be relevant to the outcome. It should be clear where the progress is in a journey towards this specific outcome, for example what activities linked to it have been undertaken or are planned to be undertaken. Evidence of impact of this progress also indicates good quality.

## Slide 32: The review frameworks - Learning
Rating level | Description of rating
Significant | The SP has displayed significant learning in relation to the TOC outcomes. They have considered what they’ve learnt in the process and have explained how their insight has shaped their activities or thinking where applicable.
Some | The SP has displayed some learning in relation to the TOC outcomes. They may have considered what they’ve learnt in the process for some, but not all, of the TOC outcomes. Alternatively, the SP has provided learning updates for all of the TOC outcomes but with little explanation of how this insight has shaped their activities or thinking.
Limited | The SP has displayed limited learning in relation to the TOC outcomes. They have not considered what they’ve learnt in the process and have not explained how their insight has shaped their activities or thinking.
None / N/A | The cell is left blank.
Prompts provided to AI to calculate Progress ratings:
Evidence and/or explanations about learning, with a score ranging from 100 when significant, to 1 when limited. The score also depends on the extensiveness of considerations about what has been learnt in the process and about how insights have shaped activities or thinking.
Learning updates should be reflective and relate to the progress update for the outcome. Any evidence of impact of the learning gathered and reflected upon is good. Learning updates are particularly strong if they illustrate a new understanding and action as a result of that.

## Slide 33: The review frameworks – quality of information on goal progress
Rating level | Description of rating
Good | Updates are considered ‘Good’ quality when they which provided thorough detail and evidence on the progress made towards the TOC outcomes. Updates should include explanations of how progress has been made. Evidence may include on how and why the TOC outcome has been achieved, providing evidence e.g. through use of factual information/ data/ research/ hyperlinks or other information sources.
Mixed | Updates are considered ‘Mixed’ quality when the detail and evidence on progress made towards TOC outcome are inconsistent, with some higher quality and some lower quality updates across entries. See ‘Good’ and ‘Needs improvement’ for a definition of higher and lower quality updates.
Needs improvement | ‘Needs improvement’ updates are those with minimal detail and evidence on the progress made towards the TOC outcomes. Updates contain little detail on how progress has been made. Claims of progress are unsubstantiated and evidence (such as factual information/ data/ research/ hyperlinks/ other) is lacking.
Prompts provided to AI to calculate Progress ratings:
Evidence and/or explanations about progress towards the outcome, with a score ranging from 100 when significant, to 1 when limited. The score depends on the steps and how they contributed to the progress towards the outcome. It could be multiple meaningful steps with good evidence and/or explanations, one or a few significant steps with extensive evidence and/or explanations, or a combination of both.
Quality of details, evidence, and explanations, that span from 100 when extensive and thorough, to 1 when limited or none.
The score also depends on how claims of progress are substantiated and on the details of how and why the outcome has been achieved.